## Feuille de route
Feuille de route - Campagne de Cybersécurité
[Nom de l'entreprise]
[Logo]
Responsable du projet :
| Date de début du projet: |  | 2018-02-10
| Date du jour : |  | 2018-03-08 | [6 empty] | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-10 | 2018-02-11 | 2018-02-12 | 2018-02-13 | 2018-02-14 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18 | 2018-02-19 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-25
[10 empty] | Semaine 0 | [6 empty] | Semaine 1 | [6 empty] | Semaine 2 | [6 empty] | Semaine 3
[10 empty] | 2018-01-29 | [6 empty] | 2018-02-05 | [6 empty] | 2018-02-12 | [6 empty] | 2018-02-19
N° | Activité | Responsable | Début | Fin | Durée (jours) | % réalisé | Effort estimé (jours) | Jours consommés | Jours restants | L | M | M | J | V | S | D | L | M | M | J | V | S | D | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Lancement | [NOM] | 2018-02-10 | 2018-02-11 | 2 |  | 0 | bar: 2018-01-29 L to 2018-02-19 S
1.1 | Diffusion e-mail teasing | [NOM] | 2018-02-10 | 2018-02-11 | 2 | 0% | 0 | 0 | 2 | bar: 2018-02-05 J; 2018-02-05 S to 2018-02-05 D
2 | Mot de Passe fort | [NOM] | 2018-02-17 | 2018-02-21 | 5 |  | 3 | bar: 2018-01-29 L to 2018-02-19 S
2.1 | Diffusion e-mail | [NOM] | 2018-02-17 | 2018-02-17 | 1 | 0% | 0 | 0 | 1 | bar: 2018-02-12 S
2.2 | Campagne d'affichage | [NOM] | 2018-02-17 | 2018-02-21 | 5 | 0% | 3 | 0 | 5 | bar: 2018-02-12 S to 2018-02-19 W
2.3 | Présentation | [NOM] | 2018-02-19 | 2018-02-19 | 1 | 0% | 1 | 0 | 1 | bar: 2018-02-19 M
3 | Hammeçonnage | [NOM] | 2018-02-24 | 2018-02-28 | 5 |  | 3 | bar: 2018-01-29 L to 2018-02-19 S
3.1 | Diffusion e-mail | [NOM] | 2018-02-24 | 2018-02-24 | 1 | 0% | 0 | 0 | 1 | bar: 2018-02-19 S
3.2 | Campagne d'affichage | [NOM] | 2018-02-24 | 2018-02-28 | 5 | 0% | 3 | 0 | 5 | bar: 2018-02-19 S to 2018-02-19 S
3.3 | Présentation | [NOM] | 2018-02-26 | 2018-02-26 | 1 | 0% | 1 | 0 | 1
4 | Ingénierie sociale | [NOM] | 2018-03-03 | 2018-03-07 | 5 |  | 3 | bar: 2018-01-29 L to 2018-02-19 S
4.1 | Diffusion e-mail | [NOM] | 2018-03-03 | 2018-03-03 | 1 | 0% | 0 | 0 | 1 | bar: 2018-02-19 T
4.2 | Campagne d'affichage | [NOM] | 2018-03-03 | 2018-03-07 | 5 | 0% | 3 | 0 | 5 | bar: 2018-02-19 T
4.3 | Présentation | [NOM] | 2018-03-05 | 2018-03-05 | 1 | 0% | 1 | 0 | 1 | bar: 2018-02-19 T to 2018-02-19 S
x

## Help
HELP |  | © 2012-2014 Vertex42 LLC
| If this Help worksheet and the info on Vertex42's website does not answer your questions: | Contact Vertex42
Intro
This Gantt Chart spreadsheet makes creating a project schedule very easy. You only need to know some basic spreadsheet operations to make this gantt chart work for you, such as how to insert, delete, copy and paste entire rows.
Be sure to read the Getting Started Tips below. It would also be a good idea to watch the demo videos on Vertex42.com. The demo videos are of the Excel version, but much of the information is applicable to the Google Sheets version as well.
Watch the Demo Videos on Vertex42.com
The Share settings for this spreadsheet must always be set to "Private"
See the TermsOfUse worksheet for more information about how you may and may not share this Gantt Chart Template.
Getting Started Tips
- | Input cells for defining the task dates and durations have a light green background. | Input Cell
- | [ Bracketed Text ] is also meant to be edited, like the project title and task descriptions.
- | Some of the labels include cell notes to provide extra help information. | Label
- | The Project Start Date determines the first week shown in the gantt chart.
- | To adjust the range of dates shown in the gantt chart, change the Display Week.
- | The red line in the gantt chart represents the date in the Today's Date cell. You can enter Today's Date manually or use the formula =TODAY()
- | To insert a new task, insert a new row, then copy/paste an existing row from the selection of Template Rows at the bottom of the worksheet.
- | Edit the Holidays worksheet to choose which dates you want to exclude from Work Days.
Cell Color Key
Input Cell | :: Indicates which set of inputs to use
Completed Task | :: In the Gantt chart, indicates the completed portion of the task
Incomplete Task | :: In the Gantt chart, indicates the incomplete portion of the task
Using the Template Rows and Choosing a WBS Level
Inserting New Tasks
1. Insert a new blank row where you want the new task to be
2. Copy the entire row you want to use from the set of template rows
3. Paste the row you copied on top of the blank row you just inserted
4. Copy and paste the WBS cell separately, based on the level (1, 2.1, 3.2.1, 4.3.2.1)
- When inserting new rows, you must copy and paste an entire row, because the cells of the Gantt chart area are formulas.
Changing the WBS Level in the WBS Column
- The WBS numbering uses a different formula for each level, but the formula does not reference any other cell in the row. So, you can copy and paste just the WBS cell that you want to use.
- If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter them if you need to.
- You can indent the task description for sub-tasks by entering spaces (until Google decides to add an indent option).
Category Tasks
- You can use tasks that are just labels, but it can be even more useful for a category task to display the minimum Start date and maximum End date of its sub tasks. This can be done using =MIN(range_of_startdates) and =MAX(range_of_enddates). An example template row is provided, but you will need to update the MIN() and MAX() formulas.
Creating Task Dependencies
- You can enter the Start date manually, or define task dependecies using a formula. Below are the most common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
- Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
- For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
- This formula is very simple: =enddate+1
- For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3 )+1
E. | Set the Start date to a number of days before or after another date.
- This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
FAQs
Q: | What is the best way to Print?
First, select all of the rows you want to print. Then, in the Print Settings, choose "Selection" and check "No Gridlines". Fit to width and print in landscape.
You also may want to hide the Days Done, Days Left, and Color columns prior to printing.
Q: | How do I only show Monday-Friday in the chart area?
You can hide the columns that show the weekends.
Q: | How do I print the entire range of dates for my project?
You would first need to add more columns to the displayed chart area. You can insert more columns to the right of the chart area and then copy and paste columns (7 at a time) to extend the display.
Note: The more columns you add to the right of the Gantt chart, the slower the recalculation speed will be, because of the number of additional formulas.
Q: | How do I calculate the %Complete for a Summary task?
The %Complete for a summary task can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work days and "complete" is a reference to the %complete for each of the subtasks.
=ARRAYFORMULA( SUMPRODUCT( workdays, complete ) / SUM ( workdays ) )
Q: | The Start date, End date, or %Complete for a Level 1 task is wrong. How do I fix it?
When using =MIN(), =MAX(), and =SUMPRODUCT(), it is easy for the references to get messed up if you move rows around or insert new rows. You should verify and fix these formulas if they are not referencing the correct ranges.
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the cells that are messed up.
Note on C1: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on C16: This is an example comment.